## Sheet1
Sprint 3 Execution (Oct 30 - Nov 3)
A = Alex, M = Mo, S = Saad, W = Won Sprint Velocity: 1 story point / day Note: backeted dependencies mean "recommended"
User Stories | Tasks | Dependencies | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Completed
U4 | T5 | T3, T4 | 2 | W:1 | W:1
U6 | T7 |  | 2 | A:1 | A:1 |  |  |  | X
| T9 | T6 | 5 | M:1 | M:1 | M:1 | M:1 | M:1
U7 | T10 | T7, T8 | 3 |  |  | A:1
| T11 | T7, T8, T9 | 5
U8 | T13 | T5, T6, T7 | 3 |  |  | S:1 | S:1 | S:1 | X
U9 | T14 |  | 5 | S:1 | S:1 | S:1 | S:1 | S:1 | X
| T15 | T9, T10, T11, T14 | 5
Changes from Planning to Execution:
Due to midterms and unforseen technical problems Won was unable to finish T5 and was not able to do T13. He estimates that he needa another 2 story points next srpint to complete T5.
Saad was able to complete T13 instead of Won as well as his own assigned task (T14)
Due to a misunderstanding Mo was not able to complete T9 completely and feels that he needs the next sprint to fully implement it
Alex was able to partially able complete T10 due to a limited time amount of time available because he had three midterms during the sprint duration. He will finish the remainder of the task during next sprint.