## Sheet1
Sprint 4 Plan (Nov 6 - Nov 10)
A = Alex, M = Mo, S = Saad, W = Won Sprint Velocity: 1 story point / day Note: backeted dependencies mean "recommended"
User Stories | Tasks | Dependencies | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Completed
U4 | T5 | T3, T4 | 2 | W:1 | W:1 |  |  |  | X
U6 | T9 | T6 | 5 | M:1 | M:1 | M:1 | M:1 | M:1 | X
U7 | T10 | T7, T8 | 3 | A:1 | A:1 | A:1 |  |  | X
| T11 | T7, T8, T9 | 5 |  |  |  | A:1 | A:1
U8 | T13 | T5, T6, T7 | 2 |  |  |  | S:1 | S:1 | X
U9 | T15 | T9, T10, T11, T14 | 3 | S:1 | S:1 | S:1 |  |  | X
Notes
Saad thinks that he will be able to complete T15 in 3 story points instead of 5 as originally estimated