## Sheet1
Sprint 6 Plan (Nov 20 - Nov 24)
A = Alex, M = Mo, S = Saad, W = Won Sprint Velocity: 1 story point / day Note: backeted dependencies mean "recommended"
User Stories | Tasks | Dependencies | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Completed
U7 | T11 | T7, T8, T9 | 1 | A:1 |  |  |  |  | X
U10 | T17 | T5 | 3 | W:1 | W:1 | W:1 |  |  | X
| T19 | T6 | 2 | M:2 | M:2 |  |  |  | X
| T20 | T7, T8, T9, T10, T11 | 1 |  | A:1 |  |  |  | X
| T21 | T7, T8, T9, T10, T11 | 4 |  |  | A:1 | A:1 | A:2 | X
| T23 | T13, T15 | 3 | S:1 | S:1 | S:1 |  |  | X
Notes