## Sheet1
Sprint 3 Plan (Oct 30 - Nov 3)
A = Alex, M = Mo, S = Saad, W = Won Sprint Velocity: 1 story point / day Note: backeted dependencies mean "recommended"
User Stories | Tasks | Dependencies | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Completed
U4 | T5 | T3, T4 | 2 | W:1 | W:1 |  |  |  | X
U6 | T7 |  | 2 | A:1 | A:1 |  |  |  | X
| T9 | T6 | 5 | M:1 | M:1 | M:1 | M:1 | M:1 | X
U7 | T10 | T7, T8 | 3 |  |  | A:1 | A:1 | A:1 | X
| T11 | T7, T8, T9 | 5
U8 | T13 | T5, T6, T7 | 3 |  |  | W:1 | W:1 | W:1 | X
U9 | T14 |  | 5 | S:1 | S:1 | S:1 | S:1 | S:1 | X
| T15 | T9, T10, T11, T14 | 5
Notes
Due to an update in plans it was found that T14 (which was previously completed) did not meet the new expectations so Saad will be completing it in this sprint