## Sheet1
Sprint 4 Execution (Nov 6 - Nov 10)
A = Alex, M = Mo, S = Saad, W = Won Sprint Velocity: 1 story point / day Note: backeted dependencies mean "recommended"
User Stories | Tasks | Dependencies | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Completed
U4 | T5 | T3, T4 | 2 | W:1 | W:1
U6 | T8 | T2 | 3 |  |  | A:1 | A:2 |  | X
| T9 | T6 | 5 | M:1 | M:1 |  | M:2 | M:1 | X
U7 | T10 | T7, T8 | 3 |  |  |  | A:1 | A:2 | X
| T11 | T7, T8, T9 | 5 |  |  |  |  | A:1
U8 | T13 | T5, T6, T7 | 3 |  |  |  | S:2 | S:1 | X
U9 | T15 | T9, T10, T11, T14 | 5 |  |  |  |  | S:1
Changes from Planning to Execution:
Won was able to almost complete T5 this sprint, he still needs 1 more story point to finish testing next sprint
Due to technical problems Alex decided to completely rework the existing report system (T8). He was still able to complete T10 but was unable to fully complete T11. He will finish it next sprint.
Due to Alex having to rework the report system, Saad was unable to complete T15 fully and will complete it next sprint.