## Sheet1
Sprint 4 Burndown
Days | 0 | 1 | 2 | 3 | 4 | 5
Provisial (in story points) | 15 | 15 | 13 | 7 | 7 | 0
Actual (in story points) | 15 | 15 | 13 | 13 | 10 | 2